## Slide 1
Update

## Slide 3: Evaluation
  Navigation
    Air Washington
    Navigation Policies and Procedures
    Data collection
  NCRC
    Update later by Sue Bradshaw
  Comparison Cohort
    South (non-WISE) vs. Bates (WISE) in the category of Manufacturing Academy

## Slide 5: Data Analyst
  The path
    Originally going to done out of house by 3rd party
      Undoable due to ESD rules
    Budget Modification needed to bring in house under Centralia IR
      IR position eliminated after President Frost’s exit
    Position will now report to Lead Program Manager
      Change in reporting and duties required data position to be re-posted
    We are planning on interviewing candidates at the end of the month

## Slide 7: Policies & Procedures
  Considered an important documents by the DOL
    This will be a living document
    First Draft is done – thanks goes to James Hovis for his steady work on this
    After revisions comments will be solicited from the consortium colleges
  Areas of concern
    Many colleges do not have their own codified Policies and Procedures
    Hopefully there will be few if any conflicts but if there are negotiating them may be tricky

## Slide 9: Site Visit
  WISE consortium’s first site visit will occur 4/11-4/14/16
  FPO Elise Wang will spend half of her time on programmatic work and half on fiscal
  She is also considering a stop off at one of the sub-recipient college on her way out – likely Renton
  We do not have an agenda or anymore details from her office at this time.

## Slide 11: Budget Update
 | Pacific Northwest Center of Excellence for Clean Energy |  |  |  |  |  |  |  | 
 | Fiscal Report Ending 12/31/15 |  |  |  |  |  |  | DATE | 2/1/2016
BUDGET STATUS |  |  |  |  |  |  |  |  | 
Sub-recipients | Yr. 1 Budget | Yr. 1 Expenditures | Yr. 1 Remaining Budget | Yr. 2 Budget | Yr. 2 Expenditures | Yr. 3 Budget | Yr. 4 Budget | Total Grant Funds | Total Remaining Budget
Centralia | $ 399,941 | 171,728 | 228,213 | 590,691 | 163,657 | 576,240 | 281,510 | 1,848,382 | 1,512,998
Everett | $ 443,619 | 203,482 | 240,137 | 469,305 | 92,302 | 460,306 | 42,546 | 1,415,776 | 1,119,992
Renton | $ 359,202 | 220,898 | 138,304 | 433,972 | 128,822 | 432,649 | 41,342 | 1,267,165 | 917,446
Green River | $ 295,012 | 82,677 | 212,335 | 416,993 | 39,585 | 406,856 | 74,556 | 1,193,417 | 1,071,155
Shoreline | $ 443,904 | 102,379 | 341,525 | 357,164 | 108,789 | 374,376 | 47,697 | 1,223,141 | 1,011,974
Bates | $ 441,283 | 243,246 | 198,037 | 327,125 | 90,818 | 328,934 | 41,300 | 1,138,642 | 804,578
S. Seattle | $ 195,698 | 99,423 | 96,275 | 255,389 | 39,663 | 222,041 | 14,536 | 687,664 | 548,578
Walla Walla | $ 603,824 | 137,421 | 466,403 | 308,220 | 168,454 | 308,623 | 0 | 1,220,667 | 914,792
Total | $ 3,182,483 | 1,261,253 | 1,921,230 | 3,158,859 | 832,089 | 3,110,025 | 543,487 | 9,994,854 | 7,901,512
Total Grant Funds for 4 years | $ 9,994,854.00 |  |  |  |  |  |  |  | 
Total Expenditures to Date | $ 2,093,342.44 |  |  |  |  |  |  |  | 
Percent of Expenditures | 20.94% |  |  |  |  |  |  |  | 
Percent of Project Time Completion | 31.25% |  |  |  |  |  |  |  |